## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | Resolved | Tractor beam | Bug | Cows are abducted when their hitboxes don't appear to be overlapping the tractor beam | BeamBehavior.cs | Winter Term | 2016-05-31 | 2016-04-19 | Problem has been resolved
2 | Resolved | Cow game objects | Feature not implemented | Cows do not fall back to the ground and continue running if the tractor beam disappears | BeamBehavior.cs, Moove.cs | 2016-03-30 | 2016-04-19 | 2016-04-19 | Problem has been resolved
3 | Resolved | Cow game objects | Feature not implemented | Cows do not disappear after they reach the edge of the screen | Moove.cs | 2016-03-30 | 2016-04-19 | 2016-04-19 | Problem has been resolved
4 | New | UFO game object | Feature not implemented | The player can move the UFO outside screen boundaries | PlayerController.cs | 2016-03-30 | 2016-04-19
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete