## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | Resolved | Tractor beam | Bug | Cows are abducted when their hitboxes don't appear to be overlapping the tractor beam | BeamBehavior.cs | Winter Term | 2016-05-31 | 2016-04-19 | Problem has been resolved
2 | Resolved | Cow game objects | Feature not implemented | Cows do not fall back to the ground and continue running if the tractor beam disappears | BeamBehavior.cs, Moove.cs | 2016-03-30 | 2016-04-19 | 2016-04-19 | Problem has been resolved
3 | Resolved | Cow game objects | Feature not implemented | Cows do not disappear after they reach the edge of the screen | Moove.cs | 2016-03-30 | 2016-04-19 | 2016-04-19 | Problem has been resolved
4 | Resolved | UFO game object | Feature not implemented | The player can move the UFO outside screen boundaries | PlayerController.cs | 2016-03-30 | 2016-04-19 | 2016-04-19 | Problem has been resolved
5 | New | Cows & Tractor beams | Bug | Cows are sometimes shown above the beam (depth) | UFOAbduction.cs | 2016-04-27 | 2016-05-04
6 | Resolved | UFO game object | Bug | The UFO slightly rises each time it hits a cow | PlayerController.cs | 2016-05-04 | 2016-05-11 | 2016-05-05 | Problem has been resolved
7 | Resolved | Cows | Bug | Cows do not despawn after touching the UFO, instead floating | Moove.cs | 2016-05-11 | 2016-05-11 | 2016-05-11 | Problem has been resolved
8 | Resolved | UFO game object | Bug | UFO rotates everytime it hits a cow | UFOAbduction.cs? | 2016-05-11 | 2016-05-11 | 2016-05-11 | Problem has been resolved
9 | Resolved | UFO game object | Bug | The UFO cannot move to the edge of the screen | PlayerController.cs | 2016-05-17 | 2016-05-18 | 2016-05-25 | Problem has been resolved
10 | Resolved | Cows | Bug | Cows spawn inside the boundary of the screen | Cow_SpawnV2 | 2016-05-17 | 2016-05-18 | 2016-05-25 | Problem has been resolved
11 | New | Cows | Bug | Cows sometimes fall past their starting height | Moove.cs | 2016-04-19 | 2016-05-18 | 2016-05-18
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete